## Slide 1
PROJECT CHARTER PITCH
HostIt
Restaurant Discovery & Promotion App
Charter overview
• Sponsor: MCDA 5510 instructors
• Project managers: Sam & Armaan
• Charter date: October 7
1

## Slide 2
Background & objective
Why this project is being undertaken
Current problem
• Restaurant information is spread across multiple sources
• Promotions may be fragmented across websites and social media
Project idea
Centralize restaurant discovery
Let customers compare restaurants
Let restaurants pay for promotions
Objective
• Build a two-sided functional prototype
• Support both customers and restaurant users
2

## Slide 3
Project scope
What the prototype will — and will not — include
In scope
• Browse, sort & filter restaurants
• Deals and specials
• Restaurant profile management
• Simulated promotional purchasing
• Restaurant database & application logic
Out of scope
• Reservations / table booking
• Food ordering or delivery
• Real payment processing
• Every third-party integration
• Commercial deployment
• Post-project maintenance
3

## Slide 4
Key deliverables
What the project will produce
1
Requirements + system design
2
Restaurant database
3
Customer interface
4
Business interface
5
Discovery + promotions
6
Functional prototype / demo
4

## Slide 5
Project timeline
October 7 → December 4
Oct 7
Charter
Oct 14
Design + database
Oct 21–28
Interfaces
Nov 4–18
Core features
Nov 25
Demo
Dec 4
Test + present
5

## Slide 6
Assumptions & constraints
Conditions the plan depends on
Key assumptions
• Enough restaurant data for testing
• Internet + location services available
• Restaurant profiles can be maintained
• Promotions can use simulated transactions
• Team remains available
Key constraints
• Academic-project timeline
• No dedicated paid-API/data budget
• Restaurant data quality & completeness
• Two-person project team
• Privacy and security requirements
6

## Slide 7
Success & governance
How the project will be judged and managed
Critical success factors
• Core customer workflow works
• Restaurant profiles can be updated
• Promotions appear in discovery
• Database stores & retrieves required data
• Final testing has no critical errors
Governance
• Sponsor / oversight: MCDA 5510 instructors
• Project team: Sam & Armaan
• External steering committee: not required
Requested outcome: Charter approval
7